## Sheet1
Web Publishing Cost Estimate
Prepared by:Mohammed Makram | Date: | 2023-06-01
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | Level 1 Totals | % of Total
1. Project Management |  |  |  | 130582.5 | 16.99%
1.1 Project manager | 720 | 50 | 36000
1.2 Project team members | 1440 | 35 | 50400
Experts and ousourcing |  |  | 44182.5
2. Hardware |  |  |  | 17500 | 2.277%
2.1 Laptops and PCs | 10 | 500 | 5000
2.2 Servers | 5 | 2500 | 12500
3. Software |  |  |  | 400750 | 52.15%
3.1 Licensed software | 5 | 150 | 750
3.2 Software development |  |  | 400000
4. Testing |  |  | 41825 | 41825 | 5.443%
5. Training and Support |  |  |  | 49700 | 6.468%
5.1 Trainee cost | 30 | 200 | 6000
5.2 Travel cost | 5 | 100 | 500
5.3 Project team members | 1440 | 30 | 43200
6. Reserves |  |  | 128071.5 | 128071.5 | 16.67%
Total project cost estimate |  |  |  | 768429

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898