## Sheet1
Risk Register for Web Publishing system
Prepared by: |  | Mohammed Makram |  |  | Date: | 2023-07-01
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 5 | Scope Creep | too many features get added | Management | The requirements did not explicitly say what is out of scope | new feature required a lot of work that was not planned | Stick to the Scope Statement | Project Manager | 10% | High | open
2 | 1 | Design Issues | Design for feature z is unable to scale | Development | The initial design was made simple as a POC | Design for feature z is unable to scale | Rework the design | Technical Lead | 20% | Low | closed
3 | 3 | Vague Requirements | feature y requirements are not clear | Management | The Analysis for that feature was not detailed enough | feature y requirements are not clear | inquire for more details | Product Owner | 30% | Medium | open
4 | 8 | Tool License Expiry | license for tool x will expire on 25th of June | Management | we estimated that we will not use the license for that long | tool x license will expire | use another tool or renew license | leader | 80% | High | open
5 | 7 | Low Stakeholder Engagement | Stakeholders do not attend meetings | Management | too many useless meetings made them lose interest | During the Sprint Review there was low stakeholder attendance | do meaningful meetings with stakeholders | leader | 50% | Medium | open
6 | 4 | Not enough seniors’ testers | we won't find enogh tgood testers to test our app and make sure it work correctly | Management | test cases not enogh | tests did not discover all bugs | Discuss with Stakeholders | leader | 15% | High | open
7 | 2 | Incorrect Budget Estimation | We are exceeding budget | Management | The Estimates were overly Optimistic | The budge was exceeded for that month | Discuss with Stakeholders | Project Manager | 20% | High | closed
8 | 6 | Inaccurate Estimations | Time estimations for development times are way off | Management | using wrong estimation techniques | feature 5.1 took more than the estimated time | reestimate durations | Technical Lead | 30% | High | open